## Sheet1
Task | Subtask | Task division | Diaconu Alexandru | Florescu Emilia | Hinoveanu Elena | Ica Alexandra | Task Status
15 Layout | 15.1 header | 15.1.1 logo |  | 40 |  |  | TBD
|  | 15.1.2 current user | 15 |  |  |  | TBD
|  | 15.1.3 user menu | 25 |  |  |  | TBD
| 15.2 body | 15.2.1 menu |  |  | 60 |  | TBD
| 15.3 footer | 15.3.1 contact details |  |  |  | 15 | TBD
|  | 15.3.2 terms & conditions |  |  |  | 7 | TBD
|  | 15.3.3 copyright |  |  |  | 5 | TBD
| Testing |  |  | 15 |  |  | TBD
1 Log in | 1.1 | 1.1.1 id | 5 |  |  |  | TBD
|  | 1.1.2 password | 5 |  |  |  | TBD
|  | 1.1.3 log in button | 5 |  |  |  | TBD
|  | link to reset password | 5 |  |  |  | TBD
|  | link to create account | 5 |  |  |  | TBD
| 1.2 error message |  |  |  |  | 7 | TBD
| Testing |  |  |  |  | 10 | TBD
2 New account | 2.1 form (text fields) | 2.1.1 |  |  |  | 5 | TBD
|  | 2.1.2 |  |  |  | 5 | TBD
|  | 2.1.3 |  |  |  | 5 | TBD
|  | 2.1.4 |  |  |  | 5 | TBD
|  | 2.1.5 |  |  |  | 5 | TBD
|  | 2.1.6 |  |  |  | 5 | TBD
|  | 2.1.7 |  |  |  | 5 | TBD
|  | 2.1.8 |  |  |  | 5 | TBD
| 2.2 submit |  |  |  |  | 5 | TBD
| 2.3 warning messages |  |  |  |  | 10 | TBD
| 2.4 terms&cond agreement |  |  |  | 5 |  | TBD
| 2.5 admin validation (just clients) |  |  |  | 7 |  | TBD
| 2.6 create account | 2.6.1 generate id & password |  |  | 30 |  | TBD
| 2.7 cancel button |  |  |  |  | 5 | TBD
| Testing |  | 20 |  |  |  | TBD
3 Password recovery | 3.1 "Forgot password" link (login) |  |  | 5 |  |  | TBD
| 3.2 form | 3.2.1 email |  | 5 |  |  | TBD
|  | 3.2.2 submit |  | 5 |  |  | TBD
|  | 3.2.3 cancel |  | 5 |  |  | TBD
| 3.3 error message |  |  | 7 |  |  | TBD
| Testing |  |  |  | 10 |  | TBD
4 View clients (admin) | 4.1 table | search button | 5 |  |  |  | TBD
|  | 4.1.2.1 | 5 |  |  |  | TBD
|  | 4.1.2.2 | 5 |  |  |  | TBD
|  | 4.1.2.3 | 5 |  |  |  | TBD
|  | 4.1.2.4 | 5 |  |  |  | TBD
|  | 4.1.2.5 | 5 |  |  |  | TBD
|  | 4.1.2.6 actions | 15 |  |  |  | TBD
| Testing |  |  | 7 | 7 |  | TBD
5 View users | 5.1 view details |  |  | 5 |  |  | TBD
|  | search button |  | 5 |  |  | TBD
| 5.2 table | 5.2.2.1 |  |  |  | 5 | TBD
|  | 5.2.2.2 |  |  |  | 5 | TBD
|  | 5.2.2.3 |  |  |  | 5 | TBD
|  | 5.2.2.4 |  |  |  | 5 | TBD
|  | 5.2.2.5 |  |  |  | 5 | TBD
|  | 5.2.2.6 |  |  |  | 5 | TBD
|  | 5.2.2.7 actions |  |  |  | 5 | TBD
| 5.3 options |  |  | 20 |  |  | TBD
| 5.4 manage |  | 5 |  |  |  | TBD
| 5.5 delete |  | 5 |  |  |  | TBD
| Testing |  |  | 7 | 7 |  | TBD
6 Search for client | 6.1 | 6.1.1 cnp | 5 |  |  |  | TBD
|  | 6.1.2 email | 5 |  |  |  | TBD
|  | 6.1.3 search | 5 |  |  |  | TBD
|  | 6.1.4 cancel | 5 |  |  |  | TBD
| Testing |  |  |  |  | 5 | TBD
7 Search for user | 7.1 | 7.1.1 |  |  | 5 |  | TBD
|  | 7.1.2 |  |  | 5 |  | TBD
|  | 7.1.3 |  |  | 5 |  | TBD
|  | 7.1.4 |  |  | 5 |  | TBD
|  | 7.1.5 |  |  | 5 |  | TBD
| Testing |  | 5 |  |  |  | TBD
8 Admin create new user | 8.1 approve request |  |  |  | 7 |  | TBD
| Testing |  |  | 3 |  |  | TBD
9 Admin validation | 9.1 approve new account |  | 7 |  |  |  | TBD
| 9.2 approve new monetary account |  | 7 |  |  |  | TBD
| Testing |  |  | 7 |  |  | TBD
10 View account details | 10.1 .1 view own details (admin & user) | 10.1.1.1 |  |  | 5 | 5 | TBD
|  | 10.1.1.2 |  |  | 5 | 5 | TBD
|  | 10.1.1.3 |  |  | 5 | 5 | TBD
|  | 10.1.1.4 |  |  | 5 | 5 | TBD
|  | 10.1.1.5 |  |  | 5 | 5 | TBD
|  | 10.1.1.6 |  |  | 5 | 5 | TBD
|  | 10.1.1.7 |  |  | 5 | 5 | TBD
| 10.2 admin view user | 10.2.1.1 | 5 |  |  |  | TBD
|  | 10.2.1.2 | 5 |  |  |  | TBD
|  | 10.2.1.3 | 5 |  |  |  | TBD
|  | 10.2.1.4 | 5 |  |  |  | TBD
|  | 10.2.1.5 | 5 |  |  |  | TBD
|  | 10.2.1.6 | 5 |  |  |  | TBD
|  | 10.2.1.7 | 5 |  |  |  | TBD
|  | 10.2.2 table |  | 40 |  |  | TBD
|  | 10.2.3 cancel |  | 5 |  |  | TBD
| 10.3 view monetary account | 10.3.1 table |  |  | 30 |  | TBD
|  | 10.3.2 transactions report |  |  | 20 |  | TBD
| 10.4 admin view client | 10.4.1 details |  | 40 |  |  | TBD
|  | 10.4.2 create account button |  | 5 |  |  | TBD
|  | 10.4.3 cancel button |  | 5 |  |  | TBD
| Testing |  | 10 |  |  | 30 | TBD
11 Edit account details | 11.1.1 edit admin details | 11.1.1.1 |  |  | 5 |  | TBD
|  | 11.1.1.2 |  |  | 5 |  | TBD
|  | 11.1.1.3 |  |  | 5 |  | TBD
|  | 11.1.1.4 save |  |  | 5 |  | TBD
|  | 11.1.1.5 cancel |  |  | 5 |  | TBD
| 11.1.2 user edit | 11.1.2.1 |  |  |  | 5 | TBD
|  | 11.1.2.2 |  |  |  | 5 | TBD
|  | 11.1.2.3 |  |  |  | 5 | TBD
|  | 11.1.2.4 |  |  |  | 5 | TBD
|  | 11.1.2.5 |  |  |  | 5 | TBD
|  | 11.1.2.6 |  |  |  | 5 | TBD
|  | 11.1.2.7 |  |  |  | 5 | TBD
|  | 11.1.2.8 |  |  |  | 5 | TBD
|  | 11.1.2.9 |  |  |  | 5 | TBD
|  | 11.1.2.10 table |  |  |  | 5 | TBD
|  | 11.1.2.11 add account button |  |  |  | 5 | TBD
|  | 11.1.2.12 save |  |  |  | 5 | TBD
|  | 11.1.2.13 cancel |  |  |  | 5 | TBD
| 11.2 cancel |  |  |  | 5 |  | TBD
| 11.3 admin edit user details | 11.3.1 | 5 |  |  |  | TBD
|  | 11.3.2 | 5 |  |  |  | TBD
|  | 11.3.3 | 5 |  |  |  | TBD
|  | 11.3.4 | 5 |  |  |  | TBD
|  | 11.3.5 | 5 |  |  |  | TBD
|  | 11.3.6 | 5 |  |  |  | TBD
|  | 11.3.7 | 5 |  |  |  | TBD
|  | 11.3.8 | 5 |  |  |  | TBD
|  | 11.3.9 table | 30 |  |  |  | TBD
|  | 11.3.10 generate new passwd | 7 |  |  |  | TBD
|  | 11.3.11 add monetary account |  | 25 |  |  | TBD
|  | 11.3.12 save | 5 |  |  |  | TBD
|  | 11.3.13 cancel | 5 |  |  |  | TBD
| Testing |  |  | 30 | 15 |  | TBD
12 Create new monetary account | 12.1 user request |  |  | 25 |  |  | TBD
| 12.2 admin add | 12.2.1 IBAN | 5 |  |  |  | TBD
|  | 12.2.2 currency (dropdown) | 7 |  |  |  | TBD
|  | 12.2.3 cancel | 5 |  |  |  | TBD
|  | 12.2.4 add | 5 |  |  |  | TBD
| Testing | [5 empty] | TBD
13 Manage monetary account | 13.1 user delete monetary account |  |  |  | 5 |  | TBD
| 13.2 admin delete monetary account |  |  |  | 5 |  | TBD
| 13.3 users (un)block account |  |  |  | 5 |  | TBD
| 13.4 admin (un)block account |  |  |  | 5 |  | TBD
| 13.5 edit account |  |  |  | 5 |  | TBD
| Testing |  | 10 |  |  |  | TBD
14 View transactions report | 14.1 view all transactions | 14.1.1 table |  |  |  | 30 | TBD
| 14.2 select account | 14.2.1 dropdown list of accounts |  |  |  | 7 | TBD
| Testing |  |  |  | 3 |  | TBD
15 Make domestic payments | 15.1 choose company | 15.1.1 dropdown |  |  | 7 |  | TBD
| 15.2 form | 15.2.1 account balance |  | 7 |  |  | TBD
|  | 15.2.2 amount |  | 5 |  |  | TBD
|  | 15.2.3 beneficiary details |  | 25 |  |  | TBD
|  | 15.2.4 beneficiary bank |  | 5 |  |  | TBD
| 15.3 choose account | 15.3.1 dropdown |  |  | 7 |  | TBD
| 15.4 bill code |  |  |  | 5 |  | TBD
| 15.5 confirm payment |  |  |  | 5 |  | TBD
| 15.6 cancel |  |  |  | 5 |  | TBD
| Testing |  | 10 |  |  |  | TBD
16 Make online transactions | 16.1 form | 16.1.1 current balance |  |  |  | 5 | TBD
|  | 16.1.2 amount |  |  |  | 5 | TBD
| 16.2 choose account | 16.2.1 dropdown |  |  |  | 7 | TBD
| 16.3 beneficiary details | 16.3.1 IBAN |  |  |  | 5 | TBD
|  | 16.3.2 name |  |  |  | 5 | TBD
|  | 16.3.3 bank |  |  |  | 5 | TBD
| 16.4 confirm payment |  |  |  |  | 5 | TBD
| 16.5 cancel |  |  |  |  | 5 | TBD
| Testing |  |  |  | 10 |  | TBD
Total time each team member |  |  | 353 | 353 | 355 | 353
|  | Time Buffer | 141
|  | TOTAL time | 1555